## Estimation Sheet
Estimation Sheet
Project: |  |  |  | Don't change
Date: |  |  |  | Fill out
Creator: |  |  |  | Optionally fill out
Actors | Weight | Amount | Weighted Value | Notes
Simple | 1 |  | 0
Average | 2 |  | 0
Complex | 3 |  | 0
Unadjusted Actor Weights |  |  | 0
Use Cases | Weight | Amount | Weighted Value | Notes
Simple | 5 |  | 0
Average | 10 |  | 0
Complex | 15 |  | 0
Unadjusted Use Case Weights |  |  | 0
Unadjusted Use Case Points |  |  | 0
Technical Factors | Weight | Applied Value | Weighted Value | Notes
Distributed system architecture | 2 |  | 0
Performance issues | 1 |  | 0
User productivity | 1 |  | 0
Complex internal processes | 1 |  | 0
Reusability of code | 1 |  | 0
Installability | 0.5 |  | 0
Usability | 0.5 |  | 0
Portability | 2 |  | 0
Maintenability | 1 |  | 0
Concurrent data access | 1 |  | 0
Security | 1 |  | 0
Third party access | 1 |  | 0
User training & adoption | 1 |  | 0
Technical Factors |  |  | 0
Technical Complexity Factor (TCF) |  |  | 0.6
Environmental Factors | Weight | Applied Value | Weighted Value | Notes | Instability Factor
Affinity with software projects | 5 |  | 0 |  | 1
Experience with similar software/applications | 5 |  | 0 |  | 1
Experience with modern software development practices | 5 |  | 0 |  | 1
Maturity of organisation, project management & change | 3 |  | 0 |  | 1
Motivation | 1 |  | 0 |  | 1
Stability of requirements | 2 |  | 0 |  | 1
Deployability | -1 |  | 0 |  | 0
Difficulty of landscape | -1 |  | 0 |  | 0
Environmental Factors |  |  | 0 |  | 6
EFactor |  |  | 1.4
Adjusted Use Case Points |  | 0
Hours per Use Case Point |  | 36
Additional Risk % | 15 | % | 0 | hour
Project Management Overhead % | 20 | % | 0 | hour
Total hours |  |  | 0 | hour
Average hourly cost | 100 | €
Total cost estimate |  |  | 0 | €
Note on B9: Actor is another system via a known and existing API
Note on B10: Actor is a system with a complex or to be developed API
Note on B11: Actor is a person using a GUI
Note on B14: Weight based on the number of transactions per use case.transacties per Use Case.
Note on B15: 3 or less transactions
Note on B16: 4 to 7 transactions
Note on B17: more than 7 transactions
Note on D21: 0 = not important 5 = essential
Note on B36: 0,06 + (0,01*Technical Factors)
Note on B39: F1 Familiar with software projects 0 The team is not familiar with software 1 The team has theoretical knowledge of software 2-3 1 or more team members have done/participated in software projects before 3-4 At least half of the team members have done/participated in software projects before 5 The entire team has been involved in various software projects
Note on B40: F2 Experience with this or similar applications 0 All team members are beginners 1-2 Some team members have some experience 3 All team members have at least 1.5 years of experience 4 Most team members have at least 2 years of experience 5 All team members are experienced
Note on B41: F3 Experience with modern software development practices 0 All programmers on the team are beginners 1 All programmers on the team have less than 1 year of experience 2-3 All programmers on the team have 1-1.5 years of experience 4 Most programmers on the team have at least 2 years of experience 5 All programmers in the team are experienced (> 2 years)
Note on B42: F4 Skills of project leader, information analyst and software architect 0 This team consists of beginners 1-2 This team has at least 1 year of experience with various projects 3-4 This team has at least 2 years of experience with various projects 5 This team has at least 3 years of experience with various projects
Note on B43: F5 Motivation 0 Not motivated 1-2 Not very motivated 3-4 Motivated to do the job well 5 Highly motivated and inspired
Note on B44: F6 Stable Requirements 0 Very unstable Requirements, constant changes 1-2 Unstable Requirements, client occasionally demands changes 3-4 Stable Requirements; small changes needed 5 Stable Requirements
Note on B45: F7 Deployability 0 All team members are fully deployable 1-2 A maximum of 20 percent is not fully deployable 3-4 Half of the team is not fully deployable 5 All team members are not fully deployable
Note on B46: F8 Difficulty of landscape 0 All programmers in the team are extremely knowledgeable about the landscape 1 Most programmers in the team have > 2 years of experience in the landscape 2 All programmers in the team have > 1.5 years of experience in the landscape 3 Most programmers on the team have > 1 year of experience in the landscape 4 Some programmers on the team have some experience in the landscape 5 All programmers on the team are beginners in the landscape

## Estimation Sheet - Example
Estimation Sheet - Example
Project: | Custom Delivery Route Calculator |  |  | Don't change
Date: | 2024-05-01 |  |  | Fill out
Creator: | John Doe |  |  | Optionally fill out
Actors | Weight | Amount | Weighted Value | Notes
Simple | 1 | 2 | 2
Average | 2 |  | 0
Complex | 3 | 10 | 30
Unadjusted Actor Weights |  |  | 32
Use Cases | Weight | Amount | Weighted Value | Notes
Simple | 5 | 4 | 20
Average | 10 | 2 | 20
Complex | 15 | 8 | 120
Unadjusted Use Case Weights |  |  | 160
Unadjusted Use Case Points |  |  | 192
Technical Factors | Weight | Applied Value | Weighted Value | Notes
Distributed system architecture | 2 | 2 | 4
Performance issues | 1 | 5 | 5
User productivity | 1 | 5 | 5
Complex internal processes | 1 | 4 | 4
Reusability of code | 1 | 1 | 1
Installability | 0.5 | 1 | 0.5
Usability | 0.5 | 5 | 2.5
Portability | 2 | 2 | 4
Maintenability | 1 | 5 | 5
Concurrent data access | 1 | 5 | 5
Security | 1 | 4 | 4
Third party access | 1 | 0 | 0
User training & adoption | 1 | 3 | 3
Technical Factors |  |  | 43
Technical Complexity Factor (TCF) |  |  | 1.03
Environmental Factors | Weight | Applied Value | Weighted Value | Notes | Instability Factor
Affinity with software projects | 5 | 4 | 20 |  | 0
Experience with similar software/applications | 5 | 4 | 20 |  | 0
Experience with modern software development practices | 5 | 3 | 15 |  | 0
Maturity of organisation, project management & change | 3 | 3 | 9 |  | 0
Motivation | 1 | 5 | 5 |  | 0
Stability of requirements | 2 | 2 | 4 |  | 1
Deployability | 1 | 4 | 4 |  | 1
Difficulty of landscape | 1 | 2 | 2 |  | 0
Environmental Factors |  |  | 79 |  | 2
EFactor |  |  | 3.77
Adjusted Use Case Points |  | 745.5552
Hours per Use Case Point |  | 20
Additional Risk % | 15 | % | 2236.6656 | hour
Project Management Overhead % | 20 | % | 447.3331 | hour
Total hours |  |  | 2683.9987 | hour
Average hourly cost | 100 | €
Total cost estimate |  |  | 268399.872 | €
Note on B9: Actor is another system via a known and existing API
Note on B10: Actor is a system with a complex or to be developed API
Note on B11: Actor is a person using a GUI
Note on B14: Weight based on the number of transactions per use case.transacties per Use Case.
Note on B15: 3 or less transactions
Note on B16: 4 to 7 transactions
Note on B17: more than 7 transactions
Note on D21: 0 = not important 5 = essential
Note on B36: 0,06 + (0,01*Technical Factors)
Note on B39: F1 Familiar with software projects 0 The team is not familiar with software 1 The team has theoretical knowledge of software 2-3 1 or more team members have done/participated in software projects before 3-4 At least half of the team members have done/participated in software projects before 5 The entire team has been involved in various software projects
Note on B40: F2 Experience with this or similar applications 0 All team members are beginners 1-2 Some team members have some experience 3 All team members have at least 1.5 years of experience 4 Most team members have at least 2 years of experience 5 All team members are experienced
Note on B41: F3 Experience with modern software development practices 0 All programmers on the team are beginners 1 All programmers on the team have less than 1 year of experience 2-3 All programmers on the team have 1-1.5 years of experience 4 Most programmers on the team have at least 2 years of experience 5 All programmers in the team are experienced (> 2 years)
Note on B42: F4 Skills of project leader, information analyst and software architect 0 This team consists of beginners 1-2 This team has at least 1 year of experience with various projects 3-4 This team has at least 2 years of experience with various projects 5 This team has at least 3 years of experience with various projects
Note on B43: F5 Motivation 0 Not motivated 1-2 Not very motivated 3-4 Motivated to do the job well 5 Highly motivated and inspired
Note on B44: F6 Stable Requirements 0 Very unstable Requirements, constant changes 1-2 Unstable Requirements, client occasionally demands changes 3-4 Stable Requirements; small changes needed 5 Stable Requirements
Note on B45: F7 Deployability 0 All team members are fully deployable 1-2 A maximum of 20 percent is not fully deployable 3-4 Half of the team is not fully deployable 5 All team members are not fully deployable
Note on B46: F8 Difficulty of landscape 0 All programmers in the team are extremely knowledgeable about the landscape 1 Most programmers in the team have > 2 years of experience in the landscape 2 All programmers in the team have > 1.5 years of experience in the landscape 3 Most programmers on the team have > 1 year of experience in the landscape 4 Some programmers on the team have some experience in the landscape 5 All programmers on the team are beginners in the landscape